## Sheet1
Milestone	Screen Name	Nature of Task	Nature of Task	Resource	HH:MM	Predecessor	Start	End
Sprint (M-2) Admin Panel
	Forgot Password	Api Creation and Integration	Forget Password Functionality for Admin	smriti.singh@mobiloitte.in	3		07/03/2018	07/03/2018
		Api Creation and Integration	Show all the Detail of Company Management in Admin panel	smriti.singh@mobiloitte.in	4		07/03/2018	07/03/2018
	Company Management	Api Creation and Integration	CRUD operation on Comapny Management	smriti.singh@mobiloitte.in	4		07/03/2018	07/04/2018
		Api Creation and Integration	Creating table for job seeker management	smriti.singh@mobiloitte.in	2		07/04/2018	07/04/2018
	Job Seeker Management	Api Creation and Integration	CRUD operation on job seeker Management	smriti.singh@mobiloitte.in	2		07/04/2018	07/04/2018
		QA	Quality Analysis	poornima.pathak@mobiloittegroup.com	8		07/05/2018	07/05/2018
		Api Creation and Integration	Show all the Detail of Job Management in Admin panel	smriti.singh@mobiloitte.in	4		07/05/2018	07/05/2018
		Api Creation and Integration	Table creation for How it works,About us , Terms and FAQ	smriti.singh@mobiloitte.in	4		07/05/2018	07/05/2018
	Static Management	Api Creation and Integration	CRUD operation on all static content table	smriti.singh@mobiloitte.in	3		07/06/2018	07/06/2018
		Api Creation and Integration	Creating table for tool and language	smriti.singh@mobiloitte.in	1		07/06/2018	07/06/2018
	Tool & Language	Api Creation and Integration	CRUD operation on tool and language	smriti.singh@mobiloitte.in	2		07/06/2018	07/06/2018
		Api Creation and Integration	Creating table for Area	smriti.singh@mobiloitte.in	1		07/06/2018	07/06/2018
	Area	Api Creation and Integration	CRUD operation on Area	smriti.singh@mobiloitte.in	3		07/06/2018	07/07/2018
		Api Creation and Integration	Creating table for Industry	smriti.singh@mobiloitte.in	1		07/07/2018	07/07/2018
		QA	Quality Analysis	poornima.pathak@mobiloittegroup.com	8		07/09/2018	07/09/2018
	Industry	Api Creation and Integration	CRUD operation on Industry	smriti.singh@mobiloitte.in	3		07/09/2018	07/09/2018
		Api Creation and Integration	Creating table for Language	smriti.singh@mobiloitte.in	2		07/09/2018	07/09/2018
	Language	Api Creation and Integration	CRUD operation on Language	smriti.singh@mobiloitte.in	3		07/09/2018	07/09/2018
	Company Management	Api Creation and Integration	Crud operation on Company Management	smriti.singh@mobiloitte.in	3		07/10/2018	07/10/2018
	Jobs Management	Api Creation and Integration	CRUD operation on Jobs Management	smriti.singh@mobiloitte.in	3		07/10/2018	07/10/2018
		Api Creation and Integration	Showing all the detail of jobs	smriti.singh@mobiloitte.in	3		07/10/2018	07/10/2018
		QA	Quality Analysis	poornima.pathak@mobiloittegroup.com	8		07/11/2018	07/11/2018
	Job Seeker Edit	Api Creation and Integration	Functionality for Edit job details	smriti.singh@mobiloitte.in	3		07/11/2018	07/11/2018
	Dashboard	Api Creation and Integration	Functionality for counting Number of Jobs,Employer,Active Job,Job seeker	smriti.singh@mobiloitte.in	3		07/11/2018	07/11/2018
	Dashboard	Api Creation and Integration	Functionality for view list of all job applicant	smriti.singh@mobiloitte.in	3		07/11/2018	07/11/2018
	Dashboard	Api Creation and Integration	Functionality for detail view of individual job applicant.	smriti.singh@mobiloitte.in	3		07/12/2018	07/12/2018
	Number Of Applicant	Api Creation and Integration	Adding pagination on admin pages	smriti.singh@mobiloitte.in	3		07/12/2018	07/12/2018
		Api Creation and Integration	Table creation for Career view request functionality	smriti.singh@mobiloitte.in	2		07/12/2018	07/12/2018
	Carrier View Request	Api Creation and Integration	Functionality for getting list of all Career view request applicant.	smriti.singh@mobiloitte.in	2		07/12/2018	07/12/2018
		QA	Quality Analysis	poornima.pathak@mobiloittegroup.com	8		07/13/2018	07/13/2018